The Schoeman Clinic — Go-Live & Payment Milestones

Aligning what unlocks each payment, and who owns each dependency

From Jess · WILBA   →   Mati Simarro (RobinHoodSolutions AI)   ·   For Dr Gina Schoeman   ·   13 July 2026

Quick note before the detail:

Tonight the shared WhatsApp inbox goes live — real progress. This note is just to get us on the same page about the rest of the build: what’s left, what unlocks the remaining balance, and which pieces are waiting on the clinic’s side vs ours. Nothing here changes the total — it only makes the finish line explicit so nobody’s guessing.

Where the money stands

| Item | Amount | When | Status |
| --- | --- | --- | --- |
| Build — kickoff | $5,000 (50%) | On kickoff | PAID |
| Build — go-live | $5,000 (50%) | On go-live | Outstanding |
| Retainer | $1,000 / mo | Min 3 months, starts at go-live | Not started |
| GHL HIPAA tier | $297 / mo | Ongoing | Gina pass-through (her cost) |

What “go-live” means in the proposal

The proposal defines go-live as all five of these being live together:

| Go-live condition | Status | Owner of what’s left |
| --- | --- | --- |
| 1. Shared WhatsApp inbox live | Live tonight | WILBA — done |
| 2. Recall / nurture campaign sent | Templates built | WILBA (draft) → Gina approves → send |
| 3. After-hours voice agent live | Not started | Blocked: Gina to top up GHL → Twilio |
| 4. Daily-brief agent live | Not started | WILBA |
| 5. Moneypenny after-hours wound down | Pending | Follows the voice agent |

Proposed: split the final $5,000 into two milestones

So client-side delays (Twilio top-up, Meta verification, KB sign-off) don’t hold up the portion WILBA fully controls, we suggest splitting the remaining balance:

| Milestone | Unlocks | Triggered when |
| --- | --- | --- |
| Milestone 2 — Operational go-live | $2,500 | All WILBA-controlled and live |
|  |  | • Shared inbox live • Recall/nurture engine live + backlog approved & sent • Patient-journey funnel live • Daily-brief agent live • Team training delivered |
| Milestone 3 — Voice go-live | $2,500 | Client-unblocked pieces live |
|  |  | • Twilio number live • Voice agent tested & live • Moneypenny after-hours wound down |

(Proposed for discussion — the total is unchanged at $10,000. This just isolates the client-dependent work into the final tranche.)

Open items owned by the clinic / Mati (these gate go-live)

Gina tops up GHL → unblocks the Twilio voice number.

Meta Business Verification / WABA migration (Meta-controlled, critical path for anything WhatsApp).

Dr Gina sign-off on the knowledge base + scripted reply library.

Compliance / legal sign-off (DPIA, consent copy) by the clinic’s data person before go-live.

Knowledge base build — Mati’s workstream, still being drafted; feeds both WhatsApp AI and the voice agent.

What WILBA delivers next (our side)

Live tonight: shared WhatsApp inbox + team training.

Next: recall / nurture / newsletter engine, draft the ~385-patient backlog campaign for Gina’s approval, build the patient-journey funnel and the daily-brief agent.

Then: voice agent as soon as the Twilio number is topped up; template everything for the incoming doctors.

The ask

Can we agree the two-milestone split above (or tell us your preferred split)?

Can you / Gina confirm the six client-side items above and roughly when each can land, so we can lock a realistic go-live date?

Prepared by Jess Morrell · WILBA (wilba.ai) · hello@wilba.ai · 13 July 2026